## Tasks
story_id | story_title | task_id | task_title | task_type | priority | status | owner_hint | dependencies | gherkin | acceptance_criteria | business_value | source_excerpt
US-001 | Streamline User Requirements Capture from Teams Calls | T-001 | Research and Select Requirements Capture Tool | Research | High | To Do | Product Owner |  | Given I am a user When I research available tools Then I should have a list of tools that meet the requirements | A list of at least 3 potential tools is created Each tool includes pros and cons Integration capabilities with Teams are evaluated | Improving the efficiency and accuracy of capturing user requirements will lead to better project alignment, reduced rework, and ultimately faster delivery of features that meet user needs. | Interviewer: Can you walk me through the pain points in capturing user requirements? User: Notes from Teams calls are manually copied into backlog items and spreadsheets. We lose nuance, repeat work, and miss acceptance criteria.
US-001 | Streamline User Requirements Capture from Teams Calls | T-002 | Integrate Selected Tool with Teams | Integration | High | To Do | Developer | T-001 | Given the selected tool is available When I integrate it with Teams Then it should capture audio and transcribe notes during calls | The tool is successfully integrated with Teams Audio from Teams calls is captured and transcribed accurately | Improving the efficiency and accuracy of capturing user requirements will lead to better project alignment, reduced rework, and ultimately faster delivery of features that meet user needs. | Interviewer: Can you walk me through the pain points in capturing user requirements? User: Notes from Teams calls are manually copied into backlog items and spreadsheets. We lose nuance, repeat work, and miss acceptance criteria.
US-001 | Streamline User Requirements Capture from Teams Calls | T-003 | Develop User Interface for Documenting Requirements | Development | High | To Do | UI/UX Designer | T-002 | Given the tool is integrated with Teams When I access the user interface Then I should be able to document nuances and acceptance criteria easily | The interface is intuitive and easy to navigate Users can document nuances and acceptance criteria without confusion | Improving the efficiency and accuracy of capturing user requirements will lead to better project alignment, reduced rework, and ultimately faster delivery of features that meet user needs. | Interviewer: Can you walk me through the pain points in capturing user requirements? User: Notes from Teams calls are manually copied into backlog items and spreadsheets. We lose nuance, repeat work, and miss acceptance criteria.
US-001 | Streamline User Requirements Capture from Teams Calls | T-004 | Implement Data Storage for Captured Requirements | Development | High | To Do | Backend Developer | T-003 | Given the user has documented requirements When I save the requirements Then they should be stored securely and be retrievable later | Requirements are stored securely Users can retrieve their documented requirements easily | Improving the efficiency and accuracy of capturing user requirements will lead to better project alignment, reduced rework, and ultimately faster delivery of features that meet user needs. | Interviewer: Can you walk me through the pain points in capturing user requirements? User: Notes from Teams calls are manually copied into backlog items and spreadsheets. We lose nuance, repeat work, and miss acceptance criteria.
US-001 | Streamline User Requirements Capture from Teams Calls | T-005 | Conduct User Testing and Gather Feedback | Testing | High | To Do | QA Tester | T-004 | Given the tool is fully developed When I conduct user testing Then I should gather feedback on its functionality and usability | User feedback is collected and documented Necessary adjustments are identified and prioritized | Improving the efficiency and accuracy of capturing user requirements will lead to better project alignment, reduced rework, and ultimately faster delivery of features that meet user needs. | Interviewer: Can you walk me through the pain points in capturing user requirements? User: Notes from Teams calls are manually copied into backlog items and spreadsheets. We lose nuance, repeat work, and miss acceptance criteria.
US-001 | Streamline User Requirements Capture from Teams Calls | T-006 | Train Users on New Process | Training | High | To Do | Product Owner | T-005 | Given the tool is ready for use When I conduct training sessions Then users should understand how to use the new process effectively | Training materials are created and distributed Users report understanding the new process after training | Improving the efficiency and accuracy of capturing user requirements will lead to better project alignment, reduced rework, and ultimately faster delivery of features that meet user needs. | Interviewer: Can you walk me through the pain points in capturing user requirements? User: Notes from Teams calls are manually copied into backlog items and spreadsheets. We lose nuance, repeat work, and miss acceptance criteria.

## Summary
metric | value
task_count | 6
story_count | 1
high_priority_tasks | 6